Steps to running a CaPRC shoot.

2-2.5 Weeks prior:

- Post announcement thread on Calguns, Snipershide etc.

- Post other threads linking to the announcement thread to draw in new attendees.

1 Week to 3 days prior:

- Start nailing down attendance to eliminate the “maybes”

- Gather a list of names to determine attendance level

- Print score sheet and waivers.

- Print out new stage description sheets and write up a few new courses of fire.

- Print targets for attendees + 25% extra for last minute add-ons.

1-2 Days prior:

- Verify which club officers are going to run the shoot on the day of the event.

- Check supply of targets, cardboard backers, stapleguns, markers & paint.

- Verify availability of portable shade, cooler, chronograph and shot timer.

- Get enough bottled water, minimum 4 bottles per person.

Day of the shoot:

- Pick up ice for the cooler

- Arrive at the Newhall Park & Ride by 7:45 to greet shooters

- Carpool to shoot location

Upon Arrival at shoot location:

- Have everyone sign-in including club waiver.

- Collect donations.

- Assess existing targets and assign people to paint steel as needed.

- Assign people to setup cardboard backers for zeroing & practice stages.

- Assign people to setup any new steel targets as needed.

- Assign people to setup shade and any firing line props as needed.

- Safety meeting to explain what to expect and how to keep things moving.

- Explain standard line commands.